## Guidelines
Sr.No | Guidelines
1 | This checklist need to be used for all Development projects tracked in ecube. For all Conversion, Technical upgrade & Migration projects, this checklist need to be customised as per the Phase wise deliverables committed in the SOW
2 | Customer review completion and signoff is mandatory if it's mentioned in the contract . If it's not mentioned, it may not be a gating criteria . Peer review completion and ERT review completion will be mandaory for all the phases which are in scope
3 | Productivity Improvement plan need to be baselined during proejct planning stage. The evidence of usage of tools/accelarators/automation as per the approved plan need to be verified during the gating assessment for all the applicable phases
4 | For all FPP projects , Re-estimation need to be done after completion of each phase and the BTG efforts need to align with POC
5 | For all Testing activites in scope ( IT/ST/UAT ) , availability of independent testing team should be checked
6 | UTC density of 40-50 UTCs /KLOC is recommended for development projects following LOC as UOM for size measurement. This guideline is not applicable for the following 1. Size UOM is other than LOC 2. Junit is used instead of manual unit test cases Projects which use Junits should have the code coverage as one of the Gating criteria
7 | As the Veloci-Q's DPM model doesn't compute the estimated defects for IT and ST phase, the process performance baselines for Phase wise error distribution from Veloci-Q need to be referred . | By phase ( Typical ) - Detected % [for Small Projects (<400 pw)] | Goal/ Target
|  | RS | 5% - 9%
8 | Any Gating status with " Conditional- Go", it's mandatory to get the ADH / VDH approval to deliver to the customer / move to the next phase | Design | 15% - 21%
|  | Implementation (CUT) | 48% - 57%
9 | Final Gating ( SQA ) mail to all stakeholders need to be uploaded in Ecube while updating the SQA gating status in Ecube | Testing (IT and ST) | 12% - 18%
|  | By phase ( Typical ) - Detected % [for Large Projects (>400 pw)] | Goal/ Target
10 | DEFECT Classification - To Check if Error type,Severity and Defect Source details are updated for all review comments and Defects in the Review log / Defect Report | RS | 5% - 9% | REFERENCE
|  | Design | 20 - 25% | Document Review
|  | Implementation (CUT) | 42 - 48% | Errors ® | ST | LC | PF | CO | DE | IC | IE | LE | OM | OT
|  | Testing (IT and ST) | 22 - 28% | Total Errors
Document Review Error Types ( For Reference )
ST-Violation of Standards
LC-Lack of Clarity
PF-Performance
CO-Cosmetic
DE-Documentation Error
LE-Logical Error
IE-Interface Error
IC-Inconsistency with other documents
OM-Omission
OT-Others
Code Review
|  |  |  | Errors ® | FN | SN | PF | IF | LE | DS | SY | EH | MM | WC | ST | RD | OT
Total Errors
Code Review Error/Defect Types ( For Reference )
FN-Functionality
SN-Syntax
PF-Performance Constraints/Limitations
IF-Interface
LE-Logical Error
DS-Data Structures
SY-Synchronization/Timing Error
EH-Error/Exception Handling
MM-Memory
IA/WC-Inadequate/Wrong Comments
ST-Violation of Standards
RD-Redundant Code
OT-Others
Severity of Errors/Defects
|  |  |  | Severity ® | Fatal | Major | Minor
Total Errors
Source of Error/Defects
|  |  |  | Work Products ® | RS | FS | DD | PS | Code | TD | CM | UD | OT
Total Defects
Source of Errors / Defects ( For Reference ) | bar: RS
RS- Requirement Specification
FS- Functional Specification
DD-Detailed Design
PS - Program Specification
CO-Code
TD-Test Design
CM-Change Management
UD-User Document
OT-Others

## Requirements Specification
Phase | Gating Check | Measurement Criterion | Artifact to be referred | Approval Authority | Actual findings | Decision - RAG
Requirements Specification | Availability of Signed SOW | Signed off SOW document Approved version of Business Requirements document baselined in the configuration management tool | Signed off SOW Approved version of BRD | Client
Availability of approved Business Requirements Document
| Usage of MPP Planning tool | • Updated version of the MPP evidenced . • Phase wise gating assessment milestone dates updated in MPP | Approved MPP
| Competency Level | Competency Level of the Existing team as per RLS should meet the below Criteria Competencey level of CORE Team - 100 % Competency level of the total team ( Core + Non-Core ) - Mimimum 80% | 1.Competency Tracker 2.RLS
| FSD gone through below review process. * Internal Review * Customer Review | 100% planned Peer review and Client review completed | 1.FSD Review Checklists | BA
|  | 100% FSD review comments are tracked to closure | 2.FSD Review log
| NFRs reviews ( Peer & Customer ) completion | 100% planned Peer review and Client review completed 100% NFR review comments are tracked to closure | NFR review Checklists Review logs | BA
| External Review is conducted | FS and NFRs reviewed by independent Group / Subject Matter Expert 100% ERT review findings are tracked to closure | ERT Audit Report | ERT Reviewer
Review log
| Defect Classification done for all Requirements Review comments ( Peer review / Customer review / ERT Review ) | Review log / Defect report updated with Error type, Severity and Defect Source ( Refer Guidelines for more details ) | Review log | BA / PM
| Requirements Traceability matrix got updated , reviewed and approved | a)100 % of the Business Requriements mapped with Functional requirements with Unique IDs b) 100% NFRs available with Quantified goals c) RTM walk through session planned with all relevent stakeholders inlcuding SQA and approved | Updated Traceability Matrix | TL /QC | Prepared
| Usage of Wipro’s DPM model to estimate the Requirements defects and actual findings to meet the estimated defect count | a.Identification of estimated Requirement defects using Wipro’s Defect Propagation Model b.Actual Requirement defects found against Prediction to be greater than 90%. | Review logs. Defect propogation Model input Sheet | QC
| Productivity Improvement Plan baselined | Usage of planned Tools / Automation /Accelerators evidenced | Productivity Plan | PM
| Re-estimation done | Allignment of BTG efforts with POC for all FPP engagements
| a.Configuration Audit done b.All the audit observations are tracked to closure | · Configuration audit conducted within three days before the milstone date. . 100 % Config.audit observations are closed | SCAR report | Tech Lead/ PM
| · Release Notes made available · All open issues are documented in the release plan | · 100 % of sections in Release notes to be updated · 100% Open Issues documented in the release note and signed off by the PM / DM. | Updated Release Notes | DM
| Review and signoff by SQA | 95% of the above criteria is met | 1.Approved version of FSD | SQA
2.Updated Review error logs
3.Updated Traceability Matrix
4.Release Notes 5. No Requirements are peding for clarification

## Design and CUT
Phase | Gating Check | Measurement Criterion | Artifact to be refered | Approval Authority | Actual findings | Decision - RAG | Remarks
High Level DESIGN | Availability of Approved and signed off Functional and Non-functional Requirement Specifications | Approved and Signed off Functional and Non-functional Requirement Specifications are baselined in Configuration Management tool | Approved version of FSD | Client | No Signoff from customer
| Usage of MPP Planning tool | • Updated version of the MPP evidenced . • Phase wise gating assessment milestone dates updated in MPP | Approved MPP
| Competency Level | Competency Level of the Existing team as per RLS should meet the below Criteria Competency level of CORE Team - 100 % Competency level of the total team ( Core + Non-Core ) - Mimimum 80% | 1.Competency Tracker 2.RLS |  | Yes
| High Level Design gone through below review process. * Internal Review * Customer Review | · 100% planned Peer review and Client review completed | 1.Design Review Checklists 2.Design Review log | Architect / Client SME | Resource model prepared and got it reviewed by customer
· 100% HLD review comments are fixed and Closed
| Defect Classification done for all HLD Review comments ( Peer review / Customer review / ERT Review ) | Review log / Defect report updated with Error type, Severity and Defect Source ( Refer Guidelines for more details ) | Review log | Architect / PM | Yes updated
| Requirements Traceability matrix got updated , reviewed and approved | (a )100% Traceability of functionalities between requirements ( Including NFRs ) and High Level Design established . (Updated Bidirectional Traceability Matrix through Business Requirements => System Requirements => High Level Design to be in place) (b) RTM walk through session planned with all relevent stakeholders inlcuding SQA and approved | Updated Traceability Matrix | QC/PM | RTM is prepared
| System Test Plan has gone through below review process. * Internal Review * Customer Review | * ST Test Plan is reviewed by independent Test Lead/ Test Manager * ST Test Plan is reviewed and approved by customer * 100% of the findings from ST Test Plan review are tracked to closure | Review logs | Client Test Lead /Test Manager | NA
CUT | Availability of approved Low Level Design Document | Approved Low Level Design Document is baselined in the configuration management tool | Approved version of Low level Design | Client | NA
| · Source code has gone through below review process. * Internal Review * Customer Review | · Usage of Standard Code review check list | 1.Code Review Checklists 2. Code Review logs | Architect / Tech Lead | Yes, Both internal and external review comments captured and implemented.
· 100% planned Peer review and Client review completed
· 100% Code review comments are fixed and Closed
| Usage of Static Analyser tool for code review | · 100 % Code review using the tool | Code Review log |  | Not used any tool | NA
· 100% Code review comments are tracked to closure
| Unit Test cases Peer review completed | 100 % Peer review completed | Unit Test Plan | TL /PM | Yes completed
|  | 100 % review comments are tracked to closure | Review logs |  | Yes completed
| ERT Review is done for the source code | Source code reviewed by independent Group / Subject Matter Expert | 1. ERT Audit Report 2. Code review log | ERT reviewer | Yes completed
100% ERT review findings are tracked to closure
| UTC Density has to be 40-50 UTCs/KLOC | UTC Density of 40-50 UTCs/KLOC is met | Unit Test Plan | TL /PM | yes validated | NA
Adequacy of Negative test cases validated
| Usage of Unit testing tools & Code Coverage for Java / .Net achieved as per the guidelines | 1 Usage of Unit Testing tools (JUNIT /NUNIT ) evidenced 2. 80 % Code coverage achieved |  | TL/PM | Not in scope for Hackothon | NA
| 100% UT test cases to be executed ( No Blocked or not run Test Cases ) and successfully passed . | 100 % Unit test cases executed 100 % Unit test cases passed | UT execution report / Logs. | Tech Lead / PM | Yes 100% unit test cases passed.
| No outstanding defects from Unit Testing. | 100 % Unit Testing defects are tracked to closure | Unit Test Error log | QC | Yes 100% unit test cases defects closed.
| Requirements Traceability matrix got updated , reviewed and approved | (a) Updated Traceability Matrix through Requirements ( Including NFRs ) => High Level Design=> Low Level Design => Low level design sections => Code Modules => UT Case IDs to be in place (b) RTM walk through session planned with all relevent stakeholders inlcuding SQA and approved | Updated Traceability Matrix | QC/PM | RTM is updated as per test cases
| Usage of Wipro’s DPM model to estimate the CUT defects and actual findings to meet the estimated defect count | a.Identification of estimated CUT defects using Wipro’s Defect Propagation Model - 60 % of the defects need to be identified through Peer reviews ( Includes Manual reviews / Code review tool findings ) | Usage of DPM Model Review logs | QC/ PM | NA | NA
b.Actual CUT defects found against Prediction to be greater than 90%.
| Defect Classification done for all Code Review comments, UT Test case review comments , IT Test cases review comments ( Peer review / Customer review / ERT Review ) and Unit Testing defects | Review log / Defect report updated with Error type, Severity and Defect Source ( Refer Guidelines for more details ) | Review log / Unit testing defect log | TL / PM | Yes updated
| IT Environment ready | 100 % Availability of IT environment |  | Test Lead / PM
| Productivity Improvement Plan baselined | Usage of planned Tools / Automation /Accelerators evidenced | Productivity Plan |  | NA
| Re-estimation done | Allignment of BTG efforts with POC for all FPP engagements | Re-Estimation Records
| · Configuration Audit done | · Configuration audit conducted within three days before the milstone date. | SCAR Report | Tech Lead / QC
| · All the audit observations are tracked to closure | · 100 % Config.audit observations are closed .
| · Release Notes made available | · 100 % of sections in Release notes to be updated | Release Notes | DM
| · All open issues are documented in the release plan | · 100% Open Issues documented in the release note and signed off by the PM / DM.
| Review and signoff by SQA | 95% of the above criteria is met |  | SQA
1.Updated Review error logs
2.Updated Tracebility Matrix
3. IT Test Plan
3.Release Notes

## Low Level Design
Phase | Gating Check | Measurement Criterion | Artifact to be refered | Approval Authority | Actual findings | Decision - RAG
Low Level DESIGN | Availability of Approved High Level Design Document | Approved High Level Design Document is baselined in Configuration Management tool | Approved Version of High Level Desgn | Client
| Usage of MPP Planning tool | • Updated version of the MPP evidenced . • Phase wise gating assessment milestone dates updated in MPP | Approved MPP
| Competency Level | Competency Level of the Existing team as per RLS should meet the below Criteria Competency level of CORE Team - 100 % Competency level of the total team ( Core + Non-Core ) - Mimimum 80% | 1.Competency Tracker 2.RLS
| Low Level Design gone through below review process. * Internal Review * Customer Review | · 100% planned Peer review and Client review completed | 1.Design Review Checklists 2.Design Review log | Architect / Client SME
· 100% LLD review comments are tracked to closure
| · External Review is conducted | 100% ERT review findings are tracked to closure | 1. ERT Audit Report 2. Design review log | ERT Reviewer
· All the review findings are tracked to closure
| Defect Classification done for all LLD Review comments ( Peer review / Customer review / ERT Review ) | Review log / Defect report updated with Error type, Severity and Defect Source ( Refer Guidelines for more details ) | Review log | Architect / PM
| Requirements Traceability matrix got updated , reviewed and approved | (a) 100% Traceability of functionalities between requirements ( Including NFRs , High Level Design and Low level design established . (Updated Bidirectional Traceability Matrix through Business Requirements => System Requirements => High Level Design => Low Level Design to be in place) (b) RTM walk through session planned with all relevent stakeholders inlcuding SQA and approved | Updated Traceability Matrix | QC/PM
| · Unit Test Plan is reviewed | 100% planned Peer review completed | Review logs | PL/QC
| · All the review findings are tracked to closure | 100 % UT Test plan Peer review comments are tracked to closure
| Usage of Wipro’s DPM model to estimate the Requirements defects and actual findings to meet the estimated defect count | a.Identification of estimated Design defects using Wipro’s Defect Propagation Model b.Actual Design defects found against Prediction to be greater than 90%. | Usage of DPM model Review logs
| Development Environment ready | Availability of Development Environment Right version of development tool available as per SOW. Availability of right Unit Testing tool |  | TL/PM
| Productivity Improvement Plan baselined | Usage of planned Tools / Automation /Accelerators evidenced | Productivity Plan
| Re-estimation done | Allignment of BTG efforts with POC for all FPP engagements | Re-Estimation Records
| · Configuration Audit done | · Configuration audit conducted within three days before the milstone date. | SCAR Report | QC/PL
| · All the audit observations are tracked to closure | · 100 % Config.audit observations are closed .
| · Release Notes made available | · 100 % of sections in Release Notes to be updated | Release Notes | PM/DM
| · All open issues are documented in the release plan | · 100 % Open Issues documented in the Release notes and signed off by the PM /DM
| Review and signoff by SQA | 95% of the above criteria is met

## CUT
Phase | Gating Check | Measurement Criterion | Artifact to be referred | Approval Authority | Actual findings | Decision - RAG
CUT | Availability of approved Low Level Design Document | Approved Low Level Design Document is baselined in the configuration management tool | Approved version of Low level Design | Client
| Usage of MPP Planning tool | • Updated version of the MPP evidenced . • Phase wise gating assessment milestone dates updated in MPP | Approved MPP
| Competency Level | Competency Level of the Existing team as per RLS should meet the below Criteria Competency level of CORE Team - 100 % Competency level of the total team ( Core + Non-Core ) - Mimimum 80% | 1.Competency Tracker 2.RLS
| · Source code has gone through below review process. * Internal Review * Customer Review | · Usage of Standard Code review check list | 1.Code Review Checklists 2. Code Review logs | Architect / Tech Lead
· 100% planned Peer review and Client review completed
· 100% Code review comments are fixed and Closed
| Usage of Static Analyser tool for code review | · 100 % Code review using the tool | Code Review log
· 100% Code review comments are tracked to closure
| Unit Test cases Peer review completed | 100 % Peer review completed | Unit Test Plan | TL /PM
|  | 100 % review comments are tracked to closure | Review logs
| ERT Review is done for the source code | Source code reviewed by independent Group / Subject Matter Expert | 1. ERT Audit Report 2. Code review log | ERT reviewer
100% ERT review findings are tracked to closure
| UTC Density has to be 40-50 UTCs/KLOC | UTC Density of 40-50 UTCs/KLOC is met | Unit Test Plan | TL /PM
Adequacy of Negative test cases validated
| Usage of Unit testing tools & Code Coverage for Java / .Net achieved as per the guidelines | 1 Usage of Unit Testing tools (JUNIT /NUNIT ) evidenced 2. 80 % Code coverage achieved |  | TL/PM
| 100% UT test cases to be executed ( No Blocked or not run Test Cases ) and successfully passed . | 100 % Unit test cases executed 100 % Unit test cases passed | UT execution report / Logs. | Tech Lead / PM
| No outstanding defects from Unit Testing. | 100 % Unit Testing defects are tracked to closure | Unit Test Error log | QC
| Requirements Traceability matrix got updated , reviewed and approved | (a) Updated Traceability Matrix through Requirements ( Including NFRs ) => High Level Design=> Low Level Design => Low level design sections => Code Modules => UT Case IDs to be in place (b) RTM walk through session planned with all relevent stakeholders inlcuding SQA and approved | Updated Traceability Matrix | QC/PM
| Usage of Wipro’s DPM model to estimate the CUT defects and actual findings to meet the estimated defect count | a.Identification of estimated CUT defects using Wipro’s Defect Propagation Model - 60 % of the defects need to be identified through Peer reviews ( Includes Manual reviews / Code review tool findings ) | Usage of DPM Model Review logs | QC/ PM
b.Actual CUT defects found against Prediction to be greater than 90%.
| IT Test cases have gone through below review process. * Internal Review * Customer Review | * IT Test cases are reviewed by Test Lead/ Test Manager * IT Test cases are reviewed and approved by customer * 100% of the findings from IT Test cases review are tracked to closure | IT Test Plan IT test cases review log | Test Lead /Architect
| Defect Classification done for all Code Review comments, UT Test case review comments , IT Test cases review comments ( Peer review / Customer review / ERT Review ) and Unit Testing defects | Review log / Defect report updated with Error type, Severity and Defect Source ( Refer Guidelines for more details ) | Review log / Unit testing defect log | TL / PM
| IT Environment ready | 100 % Availability of IT environment |  | Test Lead / PM
| Productivity Improvement Plan baselined | Usage of planned Tools / Automation /Accelerators evidenced | Productivity Plan
| Re-estimation done | Allignment of BTG efforts with POC for all FPP engagements | Re-Estimation Records
| · Configuration Audit done | · Configuration audit conducted within three days before the milstone date. | SCAR Report | Tech Lead / QC
| · All the audit observations are tracked to closure | · 100 % Config.audit observations are closed .
| · Release Notes made available | · 100 % of sections in Release notes to be updated | Release Notes | DM
| · All open issues are documented in the release plan | · 100% Open Issues documented in the release note and signed off by the PM / DM.
| Review and signoff by SQA | 95% of the above criteria is met |  | SQA
1.Updated Review error logs
2.Updated Tracebility Matrix
3. IT Test Plan
3.Release Notes

## IT
Phase | Gating Check | Measurement Criterion | Artifact to be referred | Approval Authority | Actual findings | Decision - RAG
Integration Testing | Availability of approved Integration Test Cases . IT Test environment is ready Test Data availability | Approved and signed off Integration Test Cases baselinedd in the configuration management tool. Integration test environment is set up and ready for usage for Integration Testing activities. Availability of Test data validated | IT Test Plan
| Usage of MPP Planning tool | • Updated version of the MPP evidenced . • Phase wise gating assessment milestone dates updated in MPP | Approved MPP
| Competency Level | Competency Level of the Existing team as per RLS should meet the below Criteria Competency level of CORE Team - 100 % Competency level of the total team ( Core + Non-Core ) - Mimimum 80% | 1.Competency Tracker 2.RLS
| Requirements Traceability matrix got updated , reviewed and approved | (a) 100% Traceability of functionalities between requirements ( Including NFRs), Design, Code, UT and IT Test cases established . (Updated Bidirectional Traceability Matrix through Business Requirements => System Requirements => High Level Design=> Low Level Design=> Code => Unit Test case IDs => Integration Test Case IDs to be in place) (b) RTM walk through session planned with all relevent stakeholders inlcuding SQA and approved | Updated Bidirectional Traceability Matrix document
| ERT Review is done for IT Test Cases | * IT Test cases are reviewed by independent Test Lead/ Test Group * 100% of the findings from IT Test cases review are tracked to closure | ERT Review records on IT test cases
| * IT test cases to be executed completely ( No Blocked or not run Test Cases ) and successfully passed * Any Exception in terms of completing the test cases need to be discussed with all stake holders and signed off | * 100% IT test cases to be executed ( No Blocked or not run Test Cases ) * > 95% Pass rate for all the modules | IT Execution Reports/Logs
| * Regression Strategy and Regression Test cases are available * Regression test cases to be executed completely ( No Blocked or not run Test Cases ) and successfully passed * Any Exception in terms of completing the test cases need to be discussed with all stake holders and signed off | * Regression Test cases are reviewed and signed off. 100% of the review comments tracked to closure * 100% Regression test cases to be executed ( No Blocked or not run Test Cases ) and successfully passed . * > 95% Pass rate for all the modules | Approved version of regression test cases Regrestion Test execution records/logs
| All the defects identified are tracked to closure and re-tested. Any deviation with respect to this has to be documented in Release Notes which needs to be approved by DM /SQA | * Zero outstanding show stopper, critical or High defects | Defect Reports
| Usage of process performance baselines for Phase wise error distribution to estimate the IT defects and actual findings to meet the estimated defect count | a.Identification of estimated IT defects using process performance baselines for Phase wise error distribution b.Actual IT defects found against Prediction to be greater than 90%. | Defect Reports
| ST Test cases have gone through below review process. * Internal Review * Customer Review | * ST Test cases are reviewed by Test Lead/ Test Manager * ST Test cases are reviewed and approved by customer * 100% of the findings from ST Test cases review are tracked to closure
| Defect Classification done for all IT Test case Review comments ( Peer review / Customer review / ERT Review ) , IT defects and Regression defects | Review log / Defect report updated with Error type, Severity and Defect Source ( Refer Guidelines for more details ) | Defect Reports | Test Lead /PM
| ST Environment ready | 100% Availability of ST environment |  | Test Lead / PM
| Productivity Improvement Plan baselined | Usage of planned Tools / Automation /Accelerators evidenced | Productivity Plan
| Re-estimation done | Allignment of BTG efforts with POC for all FPP engagements | Re-Estimation Records
| · Configuration Audit is done · All the configuration audit observations are tracked to closure | · Configuration audit conducted within three days before the milstone date. · 100 % Config.audit observations are closed . | SCAR Report | Tech Lead / QC
| · Release Notes made available · All open issues are documented in the release plan | · 100 % of sections in Release notes to be updated · 100% Open Issues documented in the release note and signed off by the PM / DM. | Release Notes
| Review and signoff by SQA | 95% of the above criteria is met

## ST
Phase | Gating Check | Measurement Criterion | Artifact to be referred | Approval Authority | Actual findings | Decision - RAG
System Testing | Availability of approved System Test Cases . ST Test environment is ready Test Data Availability | Approved and signed off System Test Cases baselined in the configuration management tool. Integration test environment is set up and ready for usage for Integration Testing activities. Availability of Test data validated | System Test Plan
| Usage of MPP Planning tool | • Updated version of the MPP evidenced . • Phase wise gating assessment milestone dates updated in MPP | Approved MPP
| Competency Level | Competency Level of the Existing team as per RLS should meet the below Criteria Competency level of CORE Team - 100 % Competency level of the total team ( Core + Non-Core ) - Mimimum 80% | 1.Competency Tracker 2.RLS
| Requirements Traceability matrix got updated , reviewed and approved | ( a ) 100% Traceability of functionalities between requirements ( Including NFRs ), Design, Code, UT , IT Test cases and ST Test cases established . (Updated Bidirectional Traceability Matrix through Business Requirements => System Requirements => High Level Design=> Low Level Design=> Code => Unit Test case IDs => Integration Test Case IDs => System Test case IDs to be in place) ( b ) RTM walk through session planned with all relevent stakeholders inlcuding SQA and approved | • Updated version of the MPP evidenced . • Phase wise gating assessment milestone dates updated in MPP
| ERT Review is done for ST Test Cases | * ST Test cases are reviewed by independent Test Lead/ Test Group * 100% of the findings from ST Test cases review are tracked to closure | ERT Review records on IT test cases
| * ST test cases to be executed completely ( No Blocked or not run Test Cases ) and successfully passed * Any Exception in terms of completing the test cases need to be discussed with all stake holders and signed off | * 100% ST test cases to be executed ( No Blocked or not run Test Cases ) * > 95% Pass rate for all the modules | IT Execution Reports/Logs
| * Regression Strategy and Regression Test cases are available * Regression test cases to be executed completely ( No Blocked or not run Test Cases ) and successfully passed * Any Exception in terms of completing the test cases need to be discussed with all stake holders and signed off | * Regression Test cases are reviewed and signed off. 100% of the review comments tracked to closure * 100% Regression test cases to be executed ( No Blocked or not run Test Cases ) and successfully passed . * > 95% Pass rate for all the modules | Approved version of regression test cases Regrestion Test execution records/logs
| All the defects identified are tracked to closure and re-tested. Any deviation with respect to this has to be documented in Release Notes which needs to be approved by DM /SQA | * Zero outstanding show stopper, critical or High defects | Defect Reports
| Defect Classification done for all SIT Test case Review comments ( Peer review / Customer review / ERT Review ) , SIT defects and Regression defects | Review log / Defect report updated with Error type, Severity and Defect Source ( Refer Guidelines for more details ) | Defect Reports | Test Lead /PM
| Usage of process performance baselines for Phase wise error distribution to estimate the ST defects and actual findings to meet the estimated defect count | a.Identification of estimated ST defects using process performance baselines for Phase wise error distribution b.Actual ST defects found against Prediction to be greater than 90%. | Defect Reports
| UAT Environment ready | 100% Availability of UAT environment |  | Test Lead / PM
| Productivity Improvement Plan baselined | Usage of planned Tools / Automation /Accelerators evidenced | Productivity Plan
| Re-estimation done | Allignment of BTG efforts with POC for all FPP engagements | Re-Estimation Records
| · Configuration Audit is done · All the configuration audit observations are tracked to closure | · Configuration audit conducted within three days before the milstone date. · 100 % Config.audit observations are closed . | SCAR Report | Tech Lead / QC
| · Release Notes made available · All open issues are documented in the release plan | · 100 % of sections in Release notes to be updated · 100% Open Issues documented in the release note and signed off by the PM / DM. | Release Notes
| Review and signoff by SQA | 95% of the above criteria is met